GRAMONNATI TRUST

Clean & Divine India Project

ved@gramonnati.org  |  www.gramonnati.org

Ref: GT/CDI/MMT/2026/001          Date: 12 June 2026

To,

The CSR & Sustainability Head

MakeMyTrip India Pvt. Ltd.

DLF Building No. 5, Tower B, DLF Cyber City, Gurugram, Haryana 122 002

Sub: CSR Partnership Proposal — Guilt-Free Travel Initiative: ₹10 Per Booking for Clean Destinations, Dignified Sanitation, and Livelihoods for War Widows & Ex-Servicemen

Dear Sir / Ma'am,

India's love for travel is inseparable from its heritage, spirituality, and nature — and every year, hundreds of millions of journeys crisscross this country. Yet the destinations that draw these travellers — pilgrimage towns, hill stations, beaches, heritage monuments — are overwhelmed by the waste and sanitation challenges that mass tourism leaves behind. The very places people travel to experience are degraded by the act of travelling to them.

Gramonnati Trust writes to MakeMyTrip with a proposal that is equal parts simple and transformative: a voluntary ₹10 micro-contribution at checkout — embedded seamlessly into MMT's booking flow — that gives every Indian traveller the chance to leave their destination a little cleaner and more dignified than they found it.

# 1.  About Gramonnati Trust & the Clean and Divine India Project

Gramonnati Trust is a registered charitable trust committed to rural upliftment, environmental sustainability, and community empowerment. Our flagship initiative — the Clean and Divine India (CDI) Project — deploys two proven infrastructure units at high-footfall destinations across India:

| UNIT A — Woloo Women's Powder Room | UNIT B — New Age Dry Waste-to-Pellet Plant |
| --- | --- |
| 200 sq. ft. modular sanitation unit ¦ 4 private cubicles ¦ hygiene retail ¦ solar-powered | 10 Tonnes Per Day capacity ¦ converts dry/mixed waste into RDF pellets sold to industry |
| ₹30.7 lakhs per unit ¦ 30-month payback | ₹1.50 cr per unit (franchise/SPV) ¦ ~43% investor ROI p.a. |

A distinctive and defining feature of every CDI unit is that it is operated by War Widows and Ex-Servicemen — providing dignified, stable livelihoods to individuals who have sacrificed for the nation. Each Powder Room employs 3 persons; each Pellet Plant employs 20. This is not a token gesture; it is the operational backbone of the model.

# 2.  The Guilt-Free Travel Initiative — The Proposal

We propose that MakeMyTrip integrate a simple, voluntary ₹10 contribution into its flight and hotel booking checkout flow, structured as follows:

" Add ₹10 to keep [Destination] clean and dignified. Your contribution funds waste recycling and clean toilet facilities at this destination through Gramonnati. [ ] Yes, I want guilt-free travel. (+₹10)

Key design principles of the contribution:

- Voluntary — not a surcharge; traveller opts in with a single checkbox

- Destination-tagged — traveller sees exactly which site benefits

- Transparent — real-time impact dashboard (QR-code accessible) shows pellet volumes processed, toilets maintained, and livelihoods supported

- Tax-deductible — structured under Section 80G / eligible for CSR Schedule VII pass-through for corporate travellers

- Low integration effort — standard ancillary add-on via EPS API, similar to travel insurance or carbon-offset products already live on global platforms

# 3.  The Impact Story: What ₹10 Builds

## 3.1  Waste-to-Pellet Units — Turning Trash into Clean Energy

Each New Age Dry Waste-to-Pellet unit processes 10 Tonnes Per Day of dry waste — plastic, paper, cardboard, multi-layer packaging — and converts it into Refuse-Derived Fuel (RDF) pellets sold to cement kilns, boilers, and co-generation plants as a coal substitute. At destinations currently drowning in tourist waste, this is a complete, bankable solution:

| Metric | Per Unit Per Month |
| --- | --- |
| Waste processed | 260 tonnes |
| RDF pellets produced & sold | 260 tonnes @ ₹6,000/tonne |
| Monthly revenue | ₹15.60 lakhs |
| Monthly operating profit | ₹7.23 lakhs |
| Jobs created (Ex-Servicemen priority) | 20 per unit |
| Payback period | ~25 months |
| Carbon impact | Coal displacement — carbon credits being assessed |

## 3.2  Woloo Powder Rooms — Dignity for Every Traveller

The Woloo Women's Powder Room is a 200 sq. ft. prefabricated, solar-powered sanitation unit with 4 private cubicles, zero liquid discharge (via integrated STP), a hygiene retail bay, and QR-code-enabled cleanliness ratings. It is already a commercially validated model:

| Metric | Per Unit Per Month |
| --- | --- |
| Gross revenue (usage + retail) | ₹4.95 lakhs |
| Net operating income | ₹96,250 |
| Jobs created (War Widows priority) | 3 per unit |
| Capital cost | ₹30.68 lakhs |
| Payback | ~30 months (24 months if land waived) |

## 3.3  The Human Impact: War Widows and Ex-Servicemen at the Centre

Every unit under the CDI Project is operated by War Widows and/or Ex-Servicemen. This is a deliberate and non-negotiable design choice:

| Why Ex-Servicemen & War Widows? | What the Partnership Delivers |
| --- | --- |
| Discipline, reliability, and pride of service translate directly into the rigour required for sanitation and industrial operations. | Dignified employment at ₹15,000–₹20,000/month — stable, pensionable, purposeful. |
| Their visible presence at sacred and tourist spaces carries an inherent message of honour and duty. | Skill development in industrial waste processing, sanitation management, and customer service. |
| War widows in particular face acute livelihood gaps — this project bridges that gap with empathy. | 20 Ex-Servicemen per Pellet Plant + 3 War Widows per Powder Room — scalable to hundreds of units. |

For MakeMyTrip's CSR communications, this is a story that resonates with every Indian traveller: their ₹10 does not just clean a destination — it supports a war widow's livelihood or gives an ex-soldier a second calling.

# 4.  The Numbers: What MMT's Scale Can Unlock

MakeMyTrip processes tens of millions of transactions annually. Even a conservative opt-in rate generates a destination-transformation fund of meaningful scale:

| Scenario | MMT Transactions/Year (est.) | Opt-In Rate | Annual Fund (₹) | Units Deployable |
| --- | --- | --- | --- | --- |
| Conservative | 50 million | 10% | ₹5 crore | 3 Pellet Plants + 16 Powder Rooms |
| Moderate | 50 million | 20% | ₹10 crore | 6 Pellet Plants + 33 Powder Rooms |
| Optimistic | 50 million | 35% | ₹17.5 crore | 11 Pellet Plants + 57 Powder Rooms |

Each Pellet Plant employs 20 Ex-Servicemen. Each Powder Room employs 3 War Widows. At the moderate scenario alone, this translates to 120+ Ex-Serviceman jobs and ~100 War Widow livelihoods — created directly through the act of booking travel.

# 5.  What We Are Requesting from MakeMyTrip

Gramonnati Trust respectfully requests MakeMyTrip's engagement on the following:

| # | Ask | Purpose |
| --- | --- | --- |
| 1 | In-principle approval to embed the ₹10 Guilt-Free Travel checkbox in MMT's flight/hotel checkout flow | Core mechanism for fund generation |
| 2 | MOU / CSR Partnership Agreement designating Gramonnati as execution partner for Clean Destination Infrastructure | Legal and governance framework |
| 3 | Technical workshop with MMT's product team to scope EPS API integration for ancillary contribution checkout | Seamless UX implementation |
| 4 | Joint selection of 3 pilot destinations (suggested: Varanasi, Manali, and one South India pilgrimage town) | Phase 1 proof of concept |
| 5 | Branding of Gramonnati / CDI impact reporting co-branded with MMT on the traveller-facing impact dashboard | ESG storytelling for MMT |

# 6.  What MakeMyTrip Gains

- ESG & Sustainability Leadership: Verified, transaction-linked environmental and social impact — a compelling chapter in MMT's annual sustainability report and investor communications.

- Consumer Affinity: The 'Guilt-Free Travel' badge differentiates MMT in a commoditised OTA market. Sustainability-conscious travellers — a rapidly growing segment — actively prefer platforms that enable responsible choices.

- CSR Compliance: The ₹10 pass-through can be structured to qualify under Schedule VII of the Companies Act, 2013 — supporting MMT's CSR obligations with tangible, auditable outcomes.

- Brand Story at Scale: Every booking becomes a micro-act of nation-building — cleaning a heritage site, supporting a war widow, deploying clean energy. This is the kind of brand narrative that outlasts campaigns.

- Reputational Differentiation: MMT becomes the OTA that not only takes travellers to India's most beautiful places — but actively works to keep those places beautiful.

# 7.  Alignment with National Priorities

The Guilt-Free Travel Initiative is fully aligned with:

- Swachh Bharat Mission — Ministry of Housing & Urban Affairs

- PRASHAD (Pilgrimage Rejuvenation and Spiritual Augmentation Drive) Scheme

- Plastic Waste Management Rules 2016 and EPR Framework

- National Tourism Policy 2022 — Sustainable Tourism Pillar

- India's NDCs — Waste-to-Energy and Industrial Decarbonisation

- UN SDG 6 (Clean Water & Sanitation), SDG 11 (Sustainable Cities), SDG 12 (Responsible Consumption)

# 8.  Closing

India's most beloved destinations deserve better than the indignity of litter, inadequate toilets, and overflowing waste. The solution does not require a new tax, a government scheme, or a donor with deep pockets. It requires only that millions of travellers — people who already love these places — be given a frictionless, ₹10 way to act on that love.

MakeMyTrip, as India's largest travel platform, is uniquely positioned to be the catalyst for this movement. Gramonnati is positioned to be its execution partner — on the ground, operationally accountable, and driven by a mission that puts War Widows, Ex-Servicemen, and the dignity of India's sacred and scenic destinations at its heart.

We humbly request an opportunity to present this proposal in person and explore the partnership further at a time convenient to you.

Yours faithfully,

For and on behalf of Gramonnati Trust

_________________________________

Authorised Signatory

Clean and Divine India Project | Gramonnati Trust

Date: 12 June 2026  |  Ref: GT/CDI/MMT/2026/001

Email: info@gramonnati.org  |  Website: www.gramonnati.org

Enclosures: CDI Project Brochure | Technical Feasibility Summary | Trust Registration Documents | War Widow & Ex-Servicemen Engagement Plan